## Sheet1
Task | Components | Initial Plan
|  | Primary | Timeline (possible to overlap)
Data Cleaning | train + spray | Jeremy | 2.5 days
| Weather + Test + Trap | Andy
EDA | traps + weather | Andy
| traps + spray | Jeremy
| feature engineering | Andy
Preprocessing | SkBest, Dbscan, rolling weather features, timestamp | Ivan | 2 days
modeling | bagged trees, Xgboost, logistic regression, naïve bayes, knn, random forest, extra trees | Ivan, Hong Yee | 1 day
compilation
cost-benefit analysis | cost-benefit analysis | Jeremy | 0.5 day
readme | readme | Hong Yee | 1 day
presentation | slides | all | 1 day